## Time-chart
Days | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | No of days | Status | Remark
Dates | 23 | 24 | 25 | 28 | 29 | 30 | 31 | 1 | 4 | 5 | 6 | 7 | 8 | 11 | 12 | 13 | 14 | 15 | 18 | 19 | 20 | 21 | 22 | 25 | 26 | 27 | 28 | 1 | 4 | 5 | 6 | 7 | 8 | 11 | 12 | 13 | 14 | 15 | 18 | 19 | 20 | 21 | 22 | 25 | 26 | 27 | 28 | 29
Activity 1 | Gathering Information and understanding the need | [47 empty] | 5 | Partial | Not fully initiated as per plan
Activity 2 |  |  |  | Planning for development of product | [44 empty] | 7 | Partial | Not fully initiated as per plan
Activity 3 | [10 empty] | Initiating the development | [37 empty] | 15 | Partial | Not fully initiated as per plan
Activity 4.1 | [20 empty] | Integration of the development (Verifying the functions) | [27 empty] | 10 | Partial | Not fully initiated as per plan
Activity 4.2 | [25 empty] | Integration of the development (Integration) | [22 empty] | 10 |  | Not fully initiated as per plan
Activity 5.1 | [30 empty] | Product Testing (Unit test – Feed back) | [17 empty] | 10 |  | Not fully initiated as per plan
Activity 5.2 | [38 empty] | Product Testing (Over all test) | [9 empty] | 7 |  | Not fully initiated as per plan
Activity 6 | [44 empty] | Final demo |  |  |  | 2 |  | Not fully initiated as per plan
Activity 7 | [45 empty] | Feed back and Finalisations |  |  | 3 |  | Not fully initiated as per plan
69
| Start date : 23.01.2019 | [12 empty] | End date : 29.03.2019 | [8 empty] | Over all days will be spent : 45 days excluding Saturday and Sunday. Most of the works will be parallel
Days as per calender : 66 days
Total days are as per individual activity.

## Plan4Activity
Sr No | Activities |  |  | Time Period | Remark | Status
1 | Gathering Information and understanding the need |  |  | 5 Days
| 1.1 | What is the need for OES |  |  | Not fully done survey and not documented
| 1.2 | Is any such product available ? |  |  | No survey done as well not documented
| 1.3 | Why OES is required ? |  |  | Partially understood and not documented
| 1.4 | What are the possible ways to do the activities ? |  |  | Not done clear flow and also not documented
| 1.5 | How much time it will take ?
| 1.6 | Preparing high livel document with gathered information.
2 | Planning for development of product |  |  | 7 Days
| 2.1 | What technology will be used for the development
| 2.2 | How many man power needed for the development with skill sets
| 2.3 | Phases of the product
| 2.4 | Explaining the Technical and functional flow to managment and getting approval
3 | Initiating the development
| 3.1 | Defining the tasks |  | 15 Days
|  | 3.1.1 | Script writing and reviewing with management
|  | 3.1.2 | Explaining the functions of the script
|  | 3.1.3 | Defining requirement of API and its Importance
|  | 3.1.4 | Collecting the information for API
|  | 3.1.5 | Developing the APIs
|  | 3.1.6 | Defining requirement of UI
|  | 3.1.7 | Collecting the information for UI development
|  | 3.1.8 | Developing UI
4 | Integration of the development
| 4.1 | Verifying the functions |  | 10 Days
|  | 4.1.1 | Unit test for individual scripts and verifying the output
|  | 4.1.2 | Demonstration to Management and getting feedback
|  | 4.1.3 | Unit test for individual API with fucntional flow
|  | 4.1.4 | Demonstration to Management and getting feedback
|  | 4.1.5 | Unit test for developed UI with functional testing
|  | 4.1.6 | Demonstration to Management and getting feedback
| 4.2 | Integration |  | 10 Days
|  | 4.2.1 | Integrating individual modules from script to API and to UI
|  | 4.2.2 | Testing the flow after integration
|  | 4.2.3 | Demonstration to Management and getting feedback
|  | 4.2.4 | Incorporating the feedback received from the management and improving the integration
5 | Product Testing
| 5.1 | Unit test – Feed back | Step by step testing | 10 Days
| 5.2 | Over all test | After completing the over all integration | 7 Days
6 | Final demo |  |  | 2 Days
7 | Product Release